## Project Information
THÔNG TIN DỰ ÁN AGILE
Tên dự án: | TaskSyncEnterprise
Cơ quan đào tạo: | TRƯỜNG ĐẠI HỌC NGUYỄN TẤT THÀNH VIỆN ĐÀO TẠO QUỐC TẾ NIIE
Danh sách thành viên & Vai trò:
Họ và tên | Vai trò dự án
Huỳnh Lê Thành Nhân | Product Owner
Nguyễn Đức Mạnh | Scrum Master & Developer
Nguyễn Anh Tuấn | Researcher & Document
Nguyễn Lê Huy Hoàng | Developer
Phạm Anh Tuấn | Developer

## Epic
Mã Epic | Tên Epic
EP01 | User Access & Security Control
EP02 | Employee Profiles Management
EP03 | Department Structure Management
EP04 | Project Initiation & Team Allocation
EP05 | Task Lifecycle & Kanban Board
EP06 | Team Collaboration & Communication
EP07 | Document & File Management
EP08 | Leave & Vacation Management
EP09 | Overtime Registration & Approval
EP10 | Multi-Channel Alerts & Notifications
EP11 | Performance Analytics & Reports
EP12 | System Activity & Security Auditing

## Feature
Mã Feature | Mã Epic | Tên Feature
FT01 | EP01 | Secure User Login
FT02 | EP01 | Automatic Session Renewal
FT03 | EP01 | Role Definition Layout
FT04 | EP01 | Role-Based Access Enforcement
FT05 | EP02 | Employee Profile Creation
FT06 | EP02 | Bulk Employee Data Import
FT07 | EP02 | Direct Manager Assignment
FT08 | EP03 | Department Structure Setup
FT09 | EP03 | Department Head Assignment
FT10 | EP03 | Department Transfer Approval Flow
FT11 | EP04 | Project Creation Wizard
FT12 | EP04 | Project Team Assignment Table
FT13 | EP04 | Advanced Backlog Filtering
FT14 | EP04 | Project Milestone Tracking
FT15 | EP05 | Task Kanban Board
FT16 | EP05 | Task Dependency Diagram
FT17 | EP05 | Task Decomposition
FT18 | EP05 | Task Creation Editor
FT19 | EP06 | Collaborative Comments Feed
FT20 | EP07 | Task Attachment Security
FT21 | EP07 | Bulk Document Downloader
FT22 | EP07 | Unused Files Cleanup
FT23 | EP07 | User Mention Notifications
FT24 | EP08 | Leave Request Submission
FT25 | EP08 | Leave Approvals Panel
FT26 | EP08 | Annual Leave Balance Accrual
FT27 | EP08 | Emergency Leave Cancellation
FT28 | EP09 | Overtime Request Submission
FT29 | EP09 | Overtime Approvals Panel
FT30 | EP09 | Overtime Policy Validation
FT31 | EP10 | Notification Channel Settings
FT32 | EP10 | Daily Summary Email Digest
FT33 | EP10 | Failed Notification Retry
FT34 | EP10 | Real-Time In-App Alerts
FT35 | EP11 | Operational Performance Dashboard
FT36 | EP11 | Department Resource Allocation Map
FT37 | EP11 | Custom Project Report Generator
FT38 | EP11 | Project Burnup Predictor
FT39 | EP12 | Structural Change Auditing
FT40 | EP12 | Security Audit Log Explorer

## Product Backlog
US ID | Feature ID | User Story Title | Priority | Description | Story Point | Business Value | Target Sprint
US01 | FT01 | Secure User Login | Highest | As an Employee I want to log into the system using my registered email and password securely So that I can access my workspace and perform my daily tasks without security concerns | 3 | Cao | Sprint 1
US02 | FT02 | Automatic Session Renewal | Lowest | As an Employee I want my active login session to renew automatically in the background So that I can working continuously without experiencing sudden logouts during active usage | 5 | Trung bình | Sprint 1
US03 | FT03 | Role Definition Layout | Medium | As an Administrator I want to view and configure details of different user roles and their associated permissions on a dedicated screen So that I can easily understand and customize what actions each group of users can perform in the system | 5 | Trung bình | Sprint 1
US04 | FT04 | Role-Based Access Enforcement | Medium | As an Administrator I want the system to automatically restrict page access and actions based on the user's assigned role So that unauthorized users cannot access sensitive business data or execute management actions | 8 | Trung bình | Sprint 1
US05 | FT11 | Project Creation Wizard | Medium | As a Project Manager I want to follow a step-by-step wizard to initialize a new project shell with basic details So that I can easily set up new projects without missing any crucial initial configurations | 3 | Trung bình | Sprint 1
US06 | FT12 | Project Team Assignment Table | Highest | As a Project Manager I want to allocate team members to a project using an interactive team assignment table So that I can quickly form project teams and assign roles with clear capacity management | 5 | Trung bình | Sprint 1
US07 | FT15 | Task Kanban Board | Highest | As a Team Member I want to view and manage my tasks using an interactive Kanban board grid So that I can easily track task progress, change statuses via drag-and-drop, and collaborate with my team visually | 5 | Trung bình | Sprint 1
US08 | FT21 | Bulk Document Downloader | Lowest | As an Employee I want to select multiple files within the project and download them simultaneously in a single compressed archive So that I can save time when downloading project assets instead of downloading each file individually | 5 | Cao | Sprint 1
US09 | FT05 | Employee Profile Creation | Highest | As an HR Manager I want to create new employee profiles by entering their personal and occupational details on a structured console So that I can officially register new hires into the company directory | 5 | Cao | Sprint 2
US10 | FT06 | Bulk Employee Data Import | Medium | As an HR Manager I want to upload a spreadsheet to import multiple employee records at once So that I can quickly onboard large groups of employees without manually entering each profile. | 8 | Cao | Sprint 2
US11 | FT07 | Direct Manager Assignment | Highest | As an HR Manager I want to view and assign a direct manager to an employee within their profile So that the organization's reporting hierarchy is correctly established for approvals and evaluations. | 3 | Cao | Sprint 2
US12 | FT08 | Department Structure Setup | Highest | As an HR Manager I want to define and structure the baseline organization departments So that I can organize employees into functional business units. | 5 | Cao | Sprint 2
US13 | FT09 | Department Head Assignment | Medium | As an HR Manager I want to dynamically assign or change the designated Department Head for any department So that leadership roles are kept up-to-date and approval rights are correctly routed. | 5 | Cao | Sprint 2
US14 | FT10 | Department Transfer Approval Flow | Lowest | As an HR Manager I want to initiate and manage the approval workflow when transferring an employee from one department to another So that both sending and receiving department managers can review and approve the transfer | 13 | Cao | Sprint 2
US15 | FT16 | Task Dependency Diagram | Medium | As a Project Manager I want to view and map dependencies between different tasks in a visual graph So that I can identify bottlenecks and understand the critical path of the project | 5 | Cao | Sprint 2
US16 | FT13 | Advanced Backlog Filtering | Medium | As a Project Manager I want to filter the project backlog using multiple criteria such as assignee, priority, epic, and status So that I can easily find and prioritize specific tasks during sprint planning. | 8 | Cao | Sprint 2
US17 | FT17 | Task Decomposition | Lowest | As a Team Member I want to break down a main task into smaller, manageable sub-tasks So that I can plan, track, and complete the work in incremental steps | 8 | Cao | Sprint 2
US18 | FT19 | Collaborative Comments Feed | Lowest | As a Team Member I want to write and read rich-text comments within a task's activity feed in real-time So that I can collaborate with my team members on specific tasks directly inside the work item | 8 | Cao | Sprint 2
US19 | FT18 | Task Creation Editor |  | As a Project Manager I want to create new tasks within a project by defining their title, description, priority, and initial assignee So that I can populate the backlog with actionable items for the team |  |  | Sprint 3
US20 | FT23 | User Mention Notifications |  | As a Team Member I want the system to automatically notify another user when I mention them using "@username" in a comment or document So that I can quickly draw their attention to specific topics or feedback |  |  | Sprint 3
US21 | FT22 | Unused Files Cleanup |  | As an Administrator I want the system to automatically clean up orphaned and unused document attachments periodically So that the system storage space is optimized and old, redundant draft files are deleted |  |  | Sprint 3
US22 | FT24 | Leave Request Submission |  | As an Employee I want to submit a vacation request indicating the leave type and date range through a simple submission form So that I can request time off and have my absence formally reviewed by my manager |  |  | Sprint 3
US23 | FT25 | Leave Approvals Panel |  | As a Manager I want to view a consolidated list of leave requests from my team members and approve or reject them on a dedicated panel So that I can manage team attendance and maintain sufficient operational capacity |  |  | Sprint 3
US24 | FT26 | Annual Leave Balance Accrual |  | As an HR Manager I want the system to automatically calculate and accrue annual leave balances for each employee based on company policy So that employees always have an accurate, up-to-date count of their available paid time off |  |  | Sprint 3
US25 | FT27 | Emergency Leave Cancellation |  | As an HR Manager I want to cancel an approved leave request and restore the employee's leave balance in emergency situations So that employee records remain correct when plans change due to operational emergencies |  |  | Sprint 3
US26 | FT28 | Overtime Request Submission |  | As an Employee I want employee records remain correct when plans change due to operational emergencies So that my extra work hours are recorded and sent to my manager for payment or time-off compensation |  |  | Sprint 3
US27 | FT29 | Overtime Approvals Panel |  | As a Manager I want to review and approve/reject my team members' submitted overtime hours on a dedicated panel So that I can control project costs and officially authorize overtime payments |  |  | Sprint 4
US28 | FT30 | Overtime Policy Validation |  | As an HR Manager I want the system to automatically validate overtime requests against labor policies (such as daily or weekly limits) So that the company avoids labor law violations and excessive overtime expenses |  |  | Sprint 3
US29 | FT34 | Real-Time In-App Alerts |  | As an Employee I want to receive real-time alerts inside the application for task updates, mentions, or approval statuses So that I can stay updated on critical changes instantly without checking my email |  |  | Sprint 3
US30 | FT14 | Project Milestone Tracking |  | As a Project Manager I want to define and track project milestones and overall execution state So that I can monitor progress against key deadlines and ensure the project remains on schedule |  |  | Sprint 4
US31 | FT20 | Task Attachment Security |  | As an Administrator I want the system to enforce security checks on all uploaded file attachments So that infected, malicious, or unauthorized file types are blocked from entering the system storage |  |  | Sprint 4
US32 | FT31 | Notification Channel Settings |  | As an Employee I want to customize my notification routing preferences for different events (such as web, mobile, or email) So that I only receive critical alerts on my preferred channels and avoid notification fatigue |  |  | Sprint 4
US33 | FT32 | Daily Summary Email Digest |  | As a Team Member I want to receive a single daily email summarizing all my task updates and upcoming deadlines So that I can get a consolidated view of my work schedule without receiving dozens of individual emails |  |  | Sprint 4
US34 | FT33 | Failed Notification Retry |  | As an Administrator I want the system to automatically retry sending failed notifications when third-party notification delivery services fail So that no important communication is lost due to temporary network or system outages |  |  | Sprint 4
US35 | FT35 | Operational Performance Dashboard |  | As a Project Manager I want to view an operational performance dashboard displaying active tasks, completion rates, and delay trends So that I can evaluate project health and make informed adjustments |  |  | Sprint 4
US36 | FT36 | Department Resource Allocation Map |  | As a Department Manager I want to view a resource utilization map displaying employee workloads across various projects So that I can balance workloads and prevent employee burnout or resource underutilization |  |  | Sprint 4
US37 | FT37 | Custom Project Report Generator |  | As a Project Manager I want to configure and generate a custom project report by choosing specific fields, metrics, and date ranges So that I can present tailored progress reports to executives and stakeholders |  |  | Sprint 4
US38 | FT38 | Project Burnup Predictor |  | As a Project Manager I want to view an automated Burnup chart displaying accumulated scope versus completed work over time So that I can easily visualize and predict project completion timeline based on team velocity |  |  | Sprint 4
US39 | FT39 | Structural Change Auditing |  | As an Administrator I want the system to record all structural changes (such as modifications to departments, roles, or system settings) in an immutable log So that we have a transparent, unalterable trail of configuration changes for compliance and troubleshooting |  |  | Sprint 4
US40 | FT40 | Security Audit Log Explorer |  | As an Administrator I want to search, filter, and inspect the security audit logs through an interactive explorer interface So that I can quickly investigate potential security breaches or operational errors |  |  | Sprint 4

## User Story
Mã US | Tên User Story | Mô tả chi tiết
US01 | Secure User Login | As an Employee I want to log into the system using my registered email and password securely So that I can access my workspace and perform my daily tasks without security concerns | Spritn 1
US02 | Automatic Session Renewal | As an Employee I want my active login session to renew automatically in the background So that I can working continuously without experiencing sudden logouts during active usage
US03 | Role Definition Layout | As an Administrator I want to view and configure details of different user roles and their associated permissions on a dedicated screen So that I can easily understand and customize what actions each group of users can perform in the system
US04 | Role-Based Access Enforcement | As an Administrator I want the system to automatically restrict page access and actions based on the user's assigned role So that unauthorized users cannot access sensitive business data or execute management actions
US05 | Project Creation Wizard | As a Project Manager I want to follow a step-by-step wizard to initialize a new project shell with basic details So that I can easily set up new projects without missing any crucial initial configurations
US06 | Project Team Assignment Table | As a Project Manager I want to allocate team members to a project using an interactive team assignment table So that I can quickly form project teams and assign roles with clear capacity management
US07 | Task Kanban Board | As a Team Member I want to view and manage my tasks using an interactive Kanban board grid So that I can easily track task progress, change statuses via drag-and-drop, and collaborate with my team visually
US08 | Bulk Document Downloader | As an Employee I want to select multiple files within the project and download them simultaneously in a single compressed archive So that I can save time when downloading project assets instead of downloading each file individually
US09 | Employee Profile Creation | As an HR Manager I want to create new employee profiles by entering their personal and occupational details on a structured console So that I can officially register new hires into the company directory
US10 | Bulk Employee Data Import | As an HR Manager I want to upload a spreadsheet to import multiple employee records at once So that I can quickly onboard large groups of employees without manually entering each profile (Json)(Sprint 4)
US11 | Direct Manager Assignment | As an HR Manager I want to view and assign a direct manager to an employee within their profile So that the organization's reporting hierarchy is correctly established for approvals and evaluations
US12 | Department Structure Setup | As an HR Manager I want to define and structure the baseline organization departments So that I can organize employees into functional business units
US13 | Department Head Assignment | As an HR Manager I want to dynamically assign or change the designated Department Head for any department So that leadership roles are kept up-to-date and approval rights are correctly routed
US14 | Department Transfer Approval Flow | As an HR Manager I want to initiate and manage the approval workflow when transferring an employee from one department to another So that both sending and receiving department managers can review and approve the transfer
US15 | Task Dependency Diagram | As a Project Manager I want to view and map dependencies between different tasks in a visual graph So that I can identify bottlenecks and understand the critical path of the project
US16 | Advanced Backlog Filtering | As a Project Manager I want to filter the project backlog using multiple criteria such as name of project, priority,and status So that I can easily find and prioritize specific tasks during sprint planning.
US17 | Task Decomposition | As a Team Member I want to break down a main task user story So that I can plan, track, and complete the work in incremental steps
US18 | Collaborative Comments Feed | As a Team Member I want to write and read rich-text comments within a task's activity feed in real-time So that I can collaborate with my team members on specific tasks directly inside the work item
US19 | Task Creation Editor | As a Project Manager I want to create new tasks within a project by defining their title, description, priority So that I can populate the backlog with actionable items for the team(Sprint 2) | Sprint 2
US20 | User Mention Notifications | As a Team Member I want the system to automatically notify another user when I mention them using "@username" in a comment or document So that I can quickly draw their attention to specific topics or feedback
US21 | Unused Files Cleanup | As an Administrator I want the system to automatically clean up orphaned and unused document attachments periodically So that the system storage space is optimized and old, redundant draft files are deleted
US22 | Leave Request Submission | As an Employee I want to submit a vacation request indicating the leave type and date range through a simple submission form So that I can request time off and have my absence formally reviewed by my manager
US23 | Leave Approvals Panel | As a Manager I want to view a consolidated list of leave requests from my team members and approve or reject them on a dedicated panel So that I can manage team attendance and maintain sufficient operational capacity
US24 | Annual Leave Balance Accrual | As an HR Manager I want the system to automatically calculate and accrue annual leave balances for each employee based on company policy So that employees always have an accurate, up-to-date count of their available paid time off (Sprint 4)
US25 | Emergency Leave Cancellation | As an HR Manager I want to cancel an approved leave request and restore the employee's leave balance in emergency situations (Srpint 2) So that employee records remain correct when plans change due to operational emergencies (Dinh nghia lai vi da duyet trong thoi diem)
US26 | Overtime Request Submission | As an Employee I want to log my overtime hours by filling out a submission form specifying the date, hours worked, and reason So that my extra work hours are recorded and sent to my manager for payment or time-off compensation
US27 | Overtime Approvals Panel | As a Manager I want to review and approve/reject my team members' submitted overtime hours on a dedicated panel So that I can control project costs and officially authorize overtime payments
US28 | Overtime Policy Validation | As an HR Manager I want the system to automatically validate overtime requests against labor policies (such as daily or weekly limits) So that the company avoids labor law violations and excessive overtime expenses
US29 | Real-Time In-App Alerts | As an Employee I want to receive real-time alerts inside the application for task updates, mentions, or approval statuses So that I can stay updated on critical changes instantly without checking my email
US30 | Project Milestone Tracking | As a Project Manager I want to define and track project milestones and overall execution state So that I can monitor progress against key deadlines and ensure the project remains on schedule
US31 | Task Attachment Security | As an Administrator I want the system to enforce security checks on all uploaded file attachments So that infected, malicious, or unauthorized file types are blocked from entering the system storage
US32 | Notification Channel Settings | As an Employee I want to customize my notification routing preferences for different events (such as web, mobile, or email) So that I only receive critical alerts on my preferred channels and avoid notification fatigue
US33 | Daily Summary Email Digest | As a Team Member I want to receive a single daily email summarizing all my task updates and upcoming deadlines So that I can get a consolidated view of my work schedule without receiving dozens of individual emails
US34 | Failed Notification Retry | As an Administrator I want the system to automatically retry sending failed notifications when third-party notification delivery services fail So that no important communication is lost due to temporary network or system outages(Sprint 4)
US35 | Operational Performance Dashboard | As a Project Manager I want to view an operational performance dashboard displaying active tasks, completion rates, and delay trends So that I can evaluate project health and make informed adjustments
US36 | Department Resource Allocation Map | As a Department Manager I want to view a resource utilization map displaying employee workloads across various projects So that I can balance workloads and prevent employee burnout or resource underutilization
US37 | Custom Project Report Generator | As a Project Manager I want to configure and generate a custom project report by choosing specific fields, metrics, and date ranges So that I can present tailored progress reports to executives and stakeholders
US38 | Project Burnup Predictor | As a Project Manager I want to view an automated Burnup chart displaying accumulated scope versus completed work over time So that I can easily visualize and predict project completion timeline based on team velocity
US39 | Structural Change Auditing | As an Administrator I want the system to record all structural changes (such as modifications to departments, roles, or system settings) in an immutable log So that we have a transparent, unalterable trail of configuration changes for compliance and troubleshooting(Sprint 3)
US40 | Security Audit Log Explorer | As an Administrator I want to search, filter, and inspect the security audit logs through an interactive explorer interface So that I can quickly investigate potential security breaches or operational errors (Sprint 3)

## Priority
Priority List
Highest
Medium
Lowest

## Story Point
Story Points List
1
2
3
5
8
13

## Release Plan
Giai đoạn phát hành | Mô tả gói Increment
Release 1.0 (Giữa kỳ) | Hoàn thành Sprint 1 & Sprint 2 (Authentication, Role, Department, Employee, Dashboard)
Release 2.0 (Cuối kỳ) | Hoàn thành Sprint 3 & Sprint 4 (Project, Task, Comment, Attachment, Vacation, Audit Log)

## Sprint Planning
Sprint | Mục tiêu (Goal) | Cam kết Story Points | Thời gian thực hiện (Timeline)
Sprint 1 | Thiết lập Core Auth & Danh mục tổ chức | 24 | 02/07/2026 - 16/07/2026
Sprint 2 | Hồ sơ nhân viên & Giao diện Dashboard chủ | 27 | 16/07/2026 - 30/07/2026
Sprint 3 | Quản trị dự án & Khởi tạo task | 30 | 30/07/2026 - 13/08/2026
Sprint 4 | Kanban kéo thả, comments, attachments, vacations | 42 | 13/08/2026 - 27/08/2026