## Members
Tên thành viên | Vai trò dự án | Sprint 1 Hours | Sprint 2 Hours | Sprint 3 Hours | Sprint 4 Hours
Huỳnh Lê Thành Nhân | Product Owner | 48
Nguyễn Đức Mạnh | Scrum Master & Developer | 24
Nguyễn Anh Tuấn | Researcher | 12
Nguyễn Lê Huy Hoàng | Developer | 20
Phạm Anh Tuấn | Developer | 20
| Tổng năng suất: | 124 | 0 | 0 | 0

## PriorityRef
Priority
High
Medium
Low

## StatusRef
Status
To Do
In Progress
Done

## Sprint 1
US ID | Task Name | As A | I want | So I | Assignee | Estimate | Actual | Priority | Status | Comment
US01 | Secure User Login | Employee | Log into the system using my registered email and password securely | Access my workspace and perform my daily tasks without security concerns | Huỳnh Lê Thành Nhân | 3 | 3 | High | Done | Hoàn thành đúng hạn
US01 | Automatic Session Renewal | Employee | Active login session to renew automatically in the background | Working continuously without experiencing sudden logouts during active usage | Nguyễn Đức Mạnh | 2 | 5 | Low | Done | Hoàn thành đúng hạn
US02 | Role Definition Layout | Administrator | View and configure details of different user roles and their associated permissions on a dedicated screen | Easily understand and customize what actions each group of users can perform in the system | Nguyễn Lê Huy Hoàng | 3 | 5 | Medium | Done | Hoàn thành đúng hạn
US02 | Role-Based Access Enforcement | Administrator | The system to automatically restrict page access and actions based on the user's assigned role | Unauthorized users cannot access sensitive business data or execute management actions | Nguyễn Lê Huy Hoàng | 8 | 8 | Medium | Done | Hoàn thành đúng hạn
US03 | Project Creation Wizard | Project Manager | Follow a step-by-step wizard to initialize a new project shell with basic details | Easily set up new projects without missing any crucial initial configurationE | Nguyễn Anh Tuấn | 3 | 3 | Medium | Done | Hoàn thành đúng hạn
US03 | Project Team Assignment Table | Project Manager | Allocate team members to a project using an interactive team assignment table | Quickly form project teams and assign roles with clear capacity management | Huỳnh Lê Thành Nhân | 3 | 5 | High | Done | Hoàn thành đúng hạn
US04 | Task Kanban Board | Team Member | View and manage my tasks using an interactive Kanban board grid | Easily track task progress, change statuses via drag-and-drop, and collaborate with my team visually | Huỳnh Lê Thành Nhân | 4 | 5 | High | Done | Hoàn thành đúng hạn
US04 | Bulk Document Downloader | Employee | Select multiple files within the project and download them simultaneously in a single compressed archive | Save time when downloading project assets instead of downloading each file individual | Huỳnh Lê Thành Nhân | 5 | 5 | Low | Done | Hoàn thành đúng hạn
[5 empty] | Tổng cộng: | 31 | 39
[5 empty] | Tiến độ: |  |  |  | 800%

## Sprint 2
US ID | Task Name | As A | I want | So I | Assignee | Estimate | Actual | Priority | Status | Comment
US11 | Employee Profile Creation | HR Manager | Create new employee profiles by entering their personal and occupational details on a structured console | Register new hires into the company directory | Nguyễn Đức Mạnh | 3 | 5 | High | In Progress
US11 | Bulk Employee Data Import | HR Manager | Upload a spreadsheet to import multiple employee records at once | Onboard large groups of employees without manually entering each profile | Nguyễn Anh Tuấn | 5 | 8 | Medium | In Progress
US12 | Direct Manager Assignment | HR Manager | View and assign a direct manager to an employee within their profile | The organization's reporting hierarchy is correctly established for approvals and evaluations. | Nguyễn Đức Mạnh | 4 | 3 | High | In Progress
US12 | Department Structure Setup | HR Manager | Define and structure the baseline organization department | Organize employees into functional business units | Nguyễn Đức Mạnh | 5 | 5 | High | In Progress
US13 | Department Head Assignment | HR Manager | Dynamically assign or change the designated Department Head for any department | Leadership roles are kept up-to-date and approval rights are correctly routed | Nguyễn Anh Tuấn | 5 | 5 | Medium | In Progress
US13 | Department Transfer Approval Flow | HR Manager | Initiate and manage the approval workflow when transferring an employee from one department to another | Both sending and receiving department managers can review and approve the transfer | Huỳnh Lê Thành Nhân | 8 | 13 | Low | In Progress
US14 | Task Dependency Diagram | Project Manager | View and map dependencies between different tasks in a visual graph | Identify bottlenecks and understand the critical path of the project | Huỳnh Lê Thành Nhân | 3 | 5 | Medium | In Progress
US14 | Advanced Backlog Filtering | Project Manager | Filter the project backlog using multiple criteria such as assignee, priority, epic, and status | Find and prioritize specific tasks during sprint planning | Nguyễn Lê Huy Hoàng | 5 | 8 | Medium | In Progress
US42 | Task Decomposition | Team Member | Break down a main task into smaller, manageable sub-tasks | Plan, track, and complete the work in incremental steps |  | 5 | 8 | Low
US42 | Collaborative Comments Feed | Team Member | Write and read rich-text comments within a task's activity feed in real-time | Collaborate with my team members on specific tasks directly inside the work item | Nguyễn Lê Huy Hoàng | 8 | 8 | Low | In Progress
[5 empty] | Tổng cộng: | 51 | 68
[5 empty] | Tiến độ: |  |  |  | 0%

## Sprint 3
US ID | Task Name | As A | I want | So I | Assignee | Estimate | Actual | Priority | Status | Comment
US15 | Task Creation Editor | Project Manager | Create new tasks within a project by defining their title, description, priority, and initial assignee | Populate the backlog with actionable items for the team |  |  | 4 | High | To Do
US15 | User Mention Notifications | Team Member | The system to automatically notify another user when I mention them using "@username" in a comment or document | Quickly draw their attention to specific topics or feedback |  |  | 2 | Medium | To Do
US16 | Unused Files Cleanup | Administrator | The system to automatically clean up orphaned and unused document attachments periodically | The system storage space is optimized and old, redundant draft files are deleted |  |  | 4 | High | To Do
US16 | Leave Request Submission | Employee | Submit a vacation request indicating the leave type and date range through a simple submission form | Request time off and have my absence formally reviewed by my manager |  |  | 2 | Medium | To Do
US17 | Leave Approvals Panel | Manager | View a consolidated list of leave requests from my team members and approve or reject them on a dedicated panel | Manage team attendance and maintain sufficient operational capacity |  |  | 4 | High | To Do
US17 | Annual Leave Balance Accrual | HR Manager | The system to automatically calculate and accrue annual leave balances for each employee based on company policy | Employees always have an accurate, up-to-date count of their available paid time off |  |  | 2 | Medium | To Do
US18 | Emergency Leave Cancellation | HR Manager | Cancel an approved leave request and restore the employee's leave balance in emergency situations | Employee records remain correct when plans change due to operational emergencies |  |  | 4 | High | To Do
US18 | Overtime Request Submission | Employee | Employee records remain correct when plans change due to operational emergencies | Extra work hours are recorded and sent to my manager for payment or time-off compensation |  |  | 2 | Medium | To Do
US19 | Overtime Approvals Panel | Manager | Review and approve/reject my team members' submitted overtime hours on a dedicated panel | Control project costs and officially authorize overtime payments |  |  | 4 | High | To Do
US19 | Overtime Policy Validation | HR Manager | The system to automatically validate overtime requests against labor policies (such as daily or weekly limits) | The company avoids labor law violations and excessive overtime expenses |  |  | 2 | Medium | To Do
US20 | Real-Time In-App Alerts | Employee | Receive real-time alerts inside the application for task updates, mentions, or approval statuses | Stay updated on critical changes instantly without checking my email |  |  | 4 | High | To Do
[5 empty] | Tổng cộng: | 0 | 34
[5 empty] | Tiến độ: |  |  |  | 0%

## Sprint 4
US ID | Task Name | As A | I want | So I | Assignee | Estimate | Actual | Priority | Status | Comment
US25 | Project Milestone Tracking | Project Manager | Define and track project milestones and overall execution state | Monitor progress against key deadlines and ensure the project remains on schedule |  |  |  |  | To Do
US25 | Task Attachment Security | Administrator | The system to enforce security checks on all uploaded file attachments | Infected, malicious, or unauthorized file types are blocked from entering the system storage |  |  |  |  | To Do
US26 | Notification Channel Settings | Employee | Customize my notification routing preferences for different events (such as web, mobile, or email) | Receive critical alerts on my preferred channels and avoid notification fatigue |  |  |  |  | To Do
US26 | Daily Summary Email Digest | Team Member | VIew an operational performance dashboard displaying active tasks, completion rates, and delay trends | Evaluate project health and make informed adjustments |  |  |  |  | To Do
US27 | Failed Notification Retry | Administrator | View a resource utilization map displaying employee workloads across various projects | Balance workloads and prevent employee burnout or resource underutilization |  |  |  |  | To Do
US27 | Operational Performance Dashboard | Project Manager | Configure and generate a custom project report by choosing specific fields, metrics, and date ranges | Present tailored progress reports to executives and stakeholders |  |  |  |  | To Do
US28 | Department Resource Allocation Map | Department Manager | View an automated Burnup chart displaying accumulated scope versus completed work over time | Easily visualize and predict project completion timeline based on team velocity |  |  |  |  | To Do
US28 | Custom Project Report Generator | Project Manager | Configure and generate a custom project report by choosing specific fields, metrics, and date ranges | Present tailored progress reports to executives and stakeholders |  |  |  |  | To Do
US29 | Project Burnup Predictor | Project Manager | View an automated Burnup chart displaying accumulated scope versus completed work over time | Easily visualize and predict project completion timeline based on team velocity |  |  |  |  | To Do
US29 | Structural Change Auditing | Administrator | The system to record all structural changes (such as modifications to departments, roles, or system settings) in an immutable log | Have a transparent, unalterable trail of configuration changes for compliance and troubleshooting |  |  |  |  | To Do
US30 | Security Audit Log Explorer | Administrator | Search, filter, and inspect the security audit logs through an interactive explorer interface | Quickly investigate potential security breaches or operational errors |  |  |  |  | To Do
[5 empty] | Tổng cộng: | 0 | 0
[5 empty] | Tiến độ: |  |  |  | 0%

## Daily Scrum
Ngày | Thành viên | Hôm qua làm gì | Hôm nay làm gì | Trở ngại (Blocker) | Người hỗ trợ
2026-07-02

## Burndown
Ngày | Sprint 1 Ideal | Sprint 1 Actual | Remaining SP
Ngày 0 | 64 | 64 | 13
Ngày 1 | 57.6 | 59.6 | 12
Ngày 2 | 51.2 | 53.2 | 10
Ngày 3 | 44.8 | 46.8 | 9
Ngày 4 | 38.4 | 40.4 | 8
Ngày 5 | 32 | 30 | 6
Ngày 6 | 25.6 | 23.6 | 5
Ngày 7 | 19.2 | 17.2 | 4
Ngày 8 | 12.8 | 10.8 | 3
Ngày 9 | 6.4 | 4.4 | 1
Ngày 10 | 0 | 0 | 0

## Velocity
Sprint | Cam kết SP | Hoàn thành thực tế
Sprint 1 | 24 | 24
Sprint 2 | 27 | 27
Sprint 3 | 30 | 28
Sprint 4 | 42 | 40

## Risk Register
Risk ID | Mô tả rủi ro | Xác suất | Ảnh hưởng | Biện pháp giảm thiểu | Người phụ trách | Trạng thái
R01 | Chậm tiến độ thiết kế Kanban kéo thả do sự kiện dnd | Medium | High | Tái sử dụng thư viện `@hello-pangea/dnd` đã kiểm thử | Nguyễn Lê Huy Hoàng | Open

## Sprint Review
Sprint | Mã US | Trạng thái | Phản hồi của PO | Ý kiến Stakeholders
Sprint 1 | US01 | Completed | Hoàn thành đúng cam kết và giao diện đẹp. | Chấp nhận nghiệm thu.

## Sprint Retrospective
Went Well (Glad) | Need Improvement (Sad) | Hành động cải tiến | Người phụ trách | Hạn chót | Trạng thái
Phối hợp frontend/backend rất tốt qua swagger. | Mất thời gian sửa lỗi kết nối database local. | Viết tài liệu cấu hình cổng port SQL Server local. | Phạm Anh Tuấn | 27/07/2026 | Done